## MTA Example
Project: | Zulu | [14 empty] | FORM-0003 Rev 6.0
Project Start (G0 Approval): | 2020-01-01 |  |  | Vaild date? | 43831 |  | Date-Value: | 43831
Reporting Date: | 2022-10-20 |  |  | Vaild date? | 44854 |  | Date-Value: | 44854
reporting date OR today: | 2022-10-20
Chart Title: | Zulu - Status T October JJJJ |  |  |  |  | Warning: If you use COPY/PASTE in the table below, do ALWAYS use PASTE VALUES to avoid trouble with the conditional formatting.
Milestone Title
| Project Start (G0 Approval) | A0.G1 PRD and Planning Review | A0.G2 Architecture Review | A0.G3 Tape Out Review | A0.G4 DVT Review | A0.G5 SVT Review | B0.G2 Architecture Review | B0.G3 Tape Out Review | B0.G4 DVT Review | B0.G5 SVT Review | B0.G6 PPAP Review | B0.G7 SOP Review | n/a | n/a | final reporting dates | comment / explanation of milestone shift |  | Do not touch these formulas! | [19 empty] | Date Format Check: If a date value in the lower table is not correct, we will get a 1 in this table to allow conditional formatting in the milestone table
Project Plan | 2020-01-01 | 2020-06-01 | 2020-10-01 | 2021-04-01 | 2021-08-01 | 2021-10-01 | 2021-11-01 | 2022-01-01 | 2022-04-01 | 2022-07-01 | 2022-09-01 | 2022-11-01 | [25 empty] | 43831 | 43983 | 44105 | 44287 | 44409 | 44470 | 44501 | 44562 | 44652 | 44743 | 44805 | 44866 | 0 | 0
Reporting Date (green/red) and the corresponding estimated milestone dates at the time of the report | 2020-04-01 | 2020-06-01 | 2020-10-01 | 2021-04-01 | 2021-08-01 | 2021-10-01 | 2021-11-01 | 2022-01-01 | 2022-05-01 | 2022-07-01 | 2022-09-01 | 2022-11-01 |  |  | 2020-04-01 | plan review |  | Limit X | Limit Y |  | X' | [16 empty] | 43922 | 43983 | 44105 | 44287 | 44409 | 44470 | 44501 | 44562 | 44682 | 44743 | 44805 | 44866 | 0 | 0 | 43922
| 2020-07-01 | 2020-06-01 | 2020-10-01 | 2021-04-01 | 2021-08-01 | 2021-10-01 | 2021-11-01 | 2022-01-01 | 2022-05-01 | 2022-07-01 | 2022-09-01 | 2022-11-01 |  |  | 2020-07-01 |  |  | 2020-01-01 | 2020-01-01 | A0.G1 PRD and Planning Review | 2020-01-01 | 2020-04-01 | 2020-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44013 | 43983 | 44105 | 44287 | 44409 | 44470 | 44501 | 44562 | 44682 | 44743 | 44805 | 44866 | 0 | 0 | 44013
| 2020-10-01 |  | 2020-10-01 | 2021-04-01 | 2021-08-01 | 2021-10-01 | 2021-11-01 | 2022-01-01 | 2022-05-15 | 2022-07-01 | 2022-09-01 | 2022-11-01 |  |  | 2020-10-01 |  |  | 2025-05-14 | 2025-05-14 | A0.G2 Architecture Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44105 | 0 | 44105 | 44287 | 44409 | 44470 | 44501 | 44562 | 44696 | 44743 | 44805 | 44866 | 0 | 0 | 44105
| 2021-01-01 |  |  | 2021-04-01 | 2021-08-01 | 2021-10-01 | 2021-11-01 | 2022-01-01 | 2022-05-01 | 2022-07-01 | 2022-09-01 | 2022-11-01 |  |  | 2021-01-01 |  |  |  |  | A0.G3 Tape Out Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44197 | 0 | 0 | 44287 | 44409 | 44470 | 44501 | 44562 | 44682 | 44743 | 44805 | 44866 | 0 | 0 | 44197
| 2021-04-01 |  |  | 2021-05-01 | 2021-08-31 | 2021-10-31 | 2021-12-01 | 2022-01-31 | 2022-05-31 | 2022-07-31 | 2022-10-01 | 2022-12-01 |  |  | 2021-04-01 | resource issues |  |  |  | A0.G4 DVT Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44287 | 0 | 0 | 44317 | 44439 | 44500 | 44531 | 44592 | 44712 | 44773 | 44835 | 44896 | 0 | 0 | 44287
| 2021-07-01 |  |  | 2021-05-01 | 2021-08-31 | 2021-10-31 | 2021-12-01 | 2022-01-31 | 2022-05-31 | 2022-07-31 | 2022-10-01 | 2022-12-01 |  |  | 2021-07-01 |  |  |  |  | A0.G5 SVT Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-10-01 | 2021-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44378 | 0 | 0 | 44317 | 44439 | 44500 | 44531 | 44592 | 44712 | 44773 | 44835 | 44896 | 0 | 0 | 44378
| 2021-10-01 |  |  |  | 2021-08-31 | 2021-10-31 | 2021-12-01 | 2022-01-31 | 2022-05-31 | 2022-07-31 | 2022-10-01 | 2022-12-01 |  |  | 2021-10-01 |  |  |  |  | B0.G2 Architecture Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-10-01 | 2021-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44470 | 0 | 0 | 0 | 44439 | 44500 | 44531 | 44592 | 44712 | 44773 | 44835 | 44896 | 0 | 0 | 44470
| 2022-01-01 |  |  |  |  | 2021-10-31 | 2021-12-01 | 2022-04-01 | 2022-07-30 | 2022-09-29 | 2022-11-30 | 2023-01-30 |  |  | 2022-01-01 | late customer change request |  |  |  | B0.G3 Tape Out Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-10-01 | 2022-01-01 | 2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44562 | 0 | 0 | 0 | 0 | 44500 | 44531 | 44652 | 44772 | 44833 | 44895 | 44956 | 0 | 0 | 44562
| 2022-04-01 | [6 empty] | 2022-04-01 | 2022-07-30 | 2022-09-29 | 2022-11-30 | 2023-01-30 |  |  | 2022-04-01 |  |  |  |  | B0.G4 DVT Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-10-01 | 2022-01-01 | 2022-04-01 | 2022-07-01 | 2022-07-30 | 0 | 0 | 0 | 0 | 0 | 44652 | 0 | 0 | 0 | 0 | 0 | 0 | 44652 | 44772 | 44833 | 44895 | 44956 | 0 | 0 | 44652
| 2022-07-01 | [7 empty] | 2022-07-30 | 2022-09-29 | 2022-11-30 | 2023-01-30 |  |  | 2022-07-01 |  |  |  |  | B0.G5 SVT Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-10-01 | 2022-01-01 | 2022-04-01 | 2022-07-01 | 2022-09-29 | 0 | 0 | 0 | 0 | 0 | 44743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44772 | 44833 | 44895 | 44956 | 0 | 0 | 44743
| 2022-10-01 | [7 empty] | 2022-07-30 | 2022-09-29 | 2022-11-30 | 2023-01-30 |  |  | 2022-10-01 |  |  |  |  | B0.G6 PPAP Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-10-01 | 2022-01-01 | 2022-04-01 | 2022-07-01 | 2022-10-01 | 2022-10-20 | 0 | 0 | 0 | 0 | 44835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44772 | 44833 | 44895 | 44956 | 0 | 0 | 44835
| 2022-10-20 | [9 empty] | 2022-11-30 | 2023-01-30 |  |  | 2023-01-01 |  |  |  |  | B0.G7 SOP Review | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2021-04-01 | 2021-07-01 | 2021-10-01 | 2022-01-01 | 2022-04-01 | 2022-07-01 | 2022-10-01 | 2022-10-20 | 0 | 0 | 0 | 0 | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44895 | 44956 | 0 | 0 | 44927
| 2022-10-20 | [13 empty] | 2023-04-01 |  |  |  |  | G8 | 2020-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45017
| 2022-10-20 | [13 empty] | 2023-07-01 |  |  |  |  | G9 | 2020-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45108
| 2022-10-20 | [13 empty] | 2023-10-01 | [22 empty] | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45200
| 2022-10-20 | [13 empty] | 2024-01-01 | [22 empty] | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45292
Date Format Check: check for correct date values in milestone table
[38 empty] | 43831 | 43983 | 44105 | 44287 | 44409 | 44470 | 44501 | 44562 | 44652 | 44743 | 44805 | 44866 | 0 | 0
[17 empty] | Conditional Formattings (just in case something gets messed up …): | [20 empty] | 43922 | 43983 | 44105 | 44287 | 44409 | 44470 | 44501 | 44562 | 44682 | 44743 | 44805 | 44866 | 0 | 0 | 43922
[38 empty] | 44013 | 43983 | 44105 | 44287 | 44409 | 44470 | 44501 | 44562 | 44682 | 44743 | 44805 | 44866 | 0 | 0 | 44013
[38 empty] | 44105 | 0 | 44105 | 44287 | 44409 | 44470 | 44501 | 44562 | 44696 | 44743 | 44805 | 44866 | 0 | 0 | 44105
[38 empty] | 44197 | 0 | 0 | 44287 | 44409 | 44470 | 44501 | 44562 | 44682 | 44743 | 44805 | 44866 | 0 | 0 | 44197
[38 empty] | 44287 | 0 | 0 | 44317 | 44439 | 44500 | 44531 | 44592 | 44712 | 44773 | 44835 | 44896 | 0 | 0 | 44287
[38 empty] | 44378 | 0 | 0 | 44317 | 44439 | 44500 | 44531 | 44592 | 44712 | 44773 | 44835 | 44896 | 0 | 0 | 44378
[38 empty] | 44470 | 0 | 0 | 0 | 44439 | 44500 | 44531 | 44592 | 44712 | 44773 | 44835 | 44896 | 0 | 0 | 44470
[38 empty] | 44562 | 0 | 0 | 0 | 0 | 44500 | 44531 | 44652 | 44772 | 44833 | 44895 | 44956 | 0 | 0 | 44562
[38 empty] | 44652 | 0 | 0 | 0 | 0 | 0 | 0 | 44652 | 44772 | 44833 | 44895 | 44956 | 0 | 0 | 44652
[38 empty] | 44743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44772 | 44833 | 44895 | 44956 | 0 | 0 | 44743
[38 empty] | 44835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44772 | 44833 | 44895 | 44956 | 0 | 0 | 44835
[38 empty] | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44895 | 44956 | 0 | 0 | 44927
[38 empty] | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45017
[38 empty] | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45108
[38 empty] | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45200
[38 empty] | 44854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45292
General remarks:
Enter data in yellow fields only.
Use your local date formats. Excel typically recognizes several different formats. The cells will then show the date as DD-MMM-YY.
MTA preparation:
1) Enter project name in cell C1.
2) Enter project start (Gate 0 Approval date) in cell C3.
3) Enter final reporting dates in the yellow fields in column Q.
--> for example, quarterly final reports for projects with a duration of 3 to 4 years
--> depending on the projected project duration, you may need to adjust the intervall of the final reports
--> you may also use dynamic final reporting dates, eg. move it until something happens in your schedule
4) adjust the MTA graph axis scaling (see description below)
Data Input for reporting:
1) Enter reporting date in cell C5.
2) Enter your projected milestone dates in the row where the date in column C turns RED after you defined your reporting date in cell C5.
Conditional formattings in the date table:
| 20-Oct-23 | This indicates a shift of your milestone compared to your last report. You should enter a comment in column R for clarification.
You could also make this a "final reporting date" (column Q) to track when the change actually happened.
| 20-Oct-23 | This indicates that your milestone is achieved (at the last report already, or between last report and this report). No need to enter more dates in later reports.
| 20-Oct-23 | Invalid date OR invalid date format (not recognized as a date).
final reporting dates:
These are the intended main reporting dates.
If the actual (interim) reporting date in cell C5 is "earlier than" or "equal to" the corresponding final reporting date, the date field in column C turns red.
You can work with a fixed interval for the main reporting dates or you can adjust the intervalls to focus on changes in the timeline.
Comments:
These fields can be used to explain schedule changes.
Axis Scaling for the MTA Graph:
Fixed same Minimum for X and Y: Date of the Project Start
Fixed same Maximim for X and Y: A date somewhat later than the planned Project End (to be adjusted in case of significant project delay)
What if the project exceeds the table limits?
A data reduction/compression is required (manual work, sorry for that), i.e.:
- remove less relevant earlier reporting dates to create room for more reports (required for projects with huge delay)
--> you can also change (e.g. double) the intervall for final reporting and remove the corresponding reporting dates
- remove less relevant milestones to create room for new milestones (required for additional respins)
Sheet Protection / Cell Protection:
If you find an error in formulas or formatting, and know how to fix it, you can remove the sheet protection using the password: bettercallthomas
Please reactivate the sheet protection afterwards using the same password.
Please contact Thomas to update/fix the template.
Formulas:
Zulu = IF([Zulu, row above]=0,TODAY(),[Zulu, row above])
Reporting Dates
Milestone Dates
Note on Q13: Author: final reporting dates, see also "read me" sheet; please enter dates in ALL yellow cells of this column

## MTA Template
Project: | xyz | [14 empty] | FORM-0003 Rev 6.0
Project Start (G0 Approval): |  |  |  | Vaild date? | 0 |  | Date-Value: | 0
Reporting Date: |  |  |  | Vaild date? | 0 |  | Date-Value: | 0
reporting date OR today: | 2025-05-13
Chart Title: | xyz - Status T May JJJJ |  |  |  |  | Warning: If you use COPY/PASTE in the table below, do ALWAYS use PASTE VALUES to avoid trouble with the conditional formatting.
Milestone Title
| Project Start (G0 Approval) | A0.G1 PRD and Planning Review | A0.G2 Architecture Review | A0.G3 Tape Out Review | A0.G4 DVT Review | A0.G5 SVT Review | B0.G2 Architecture Review | B0.G3 Tape Out Review | B0.G4 DVT Review | B0.G5 SVT Review | B0.G6 PPAP Review | B0.G7 SOP Review | n/a | n/a | final reporting dates | comment / explanation of milestone shift |  | Do not touch these formulas! | [19 empty] | Date Format Check: If a date value in the lower table is not correct, we will get a 1 in this table to allow conditional formatting in the milestone table
Project Plan | 2025-05-12 | [36 empty] | 45789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reporting Date (green/red) and the corresponding estimated milestone dates at the time of the report | 0 | [16 empty] | Limit X | Limit Y |  | X' | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [16 empty] | 2025-05-12 | 2025-05-12 | A0.G1 PRD and Planning Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [16 empty] | 2025-05-14 | 2025-05-14 | A0.G2 Architecture Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | A0.G3 Tape Out Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | A0.G4 DVT Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | A0.G5 SVT Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | B0.G2 Architecture Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | B0.G3 Tape Out Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | B0.G4 DVT Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | B0.G5 SVT Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | B0.G6 PPAP Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | B0.G7 SOP Review | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | G8 | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [18 empty] | G9 | 2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Date Format Check: check for correct date values in milestone table
[38 empty] | 45789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | Conditional Formattings (just in case something gets messed up …): | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
xyz = IF([xyz, row above]=0,TODAY(),[xyz, row above])
Reporting Dates
Milestone Dates
Note on Q13: Author: final reporting dates, see also "read me" sheet; please enter dates in ALL yellow cells of this column

## Project Gate Tracker
FORM-0003 Rev 6.0
Gate Milestone Checklist
Project Name:
indie Part Number:
Customer Name:
Gate# | Planned Review date | Actual Review date | Gate review result | Attendees Milestone Participants (Project Core Team and list of people that need to sign the review per SOP-0007)
Gate 0 |  | 2021-12-10 | Approved | <PGM> | <PM> | <CL> | <SYS> | <QA>
Gate 0.8 |  |  | Skipped | <PGM> | <PM> | <CL> | <SYS> | <QA>
Gate 1 |  | 2021-05-18 | Rejected | <PGM> | <PM> | <CL> | <SYS> | <QA>
Gate 1.1 |  | 2021-07-21 | Approved with Actions | <PGM> | <PM> | <CL> | <SYS> | <QA>
Gate 2 |  | 2021-08-01 | Approved | <PGM> | <PM> | <CL> | <SYS> | <QA>
Gate 3 |  | 2021-10-01 | Approved | <PGM> | <PM> | <CL> | <SYS> | <QA>
Gate 4
Gate 5
Gate 6
Gate 7
Gate 8
Note1: Green text reflects an example and should be replaced with actual data. Aside from G0.8, and gates to be redone have revisions shown as decimals.
Note2: Attendees are generally recorded in the power point presentation. No need to duplicate if that is the case.
Note3: Signatures are collected through docusign.
Note on E13: ====== ID#AAAAWb5Rcto Lionel (2022-03-03 03:16:48) Approved with actions=conditional approval

## G0
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 0 |  | NEW PRODUCT DISCOVERY GATE REVIEW |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G0-1 | Project Scope | Initial Project Scope defined (high level) | Product Manager provides initial Schedule target from G0 to G6. | [20 empty] | R | [7 empty] | A |  |  |  | Low/No Risk | Completed
G0-2 | Critical Success Factors | List Critical Success Factors. Not limited to: Cost, Time to market, Power, Innovation, BOM reduction | This list of Success Factors will be used in G1-5.6 to create the Project KPIs that will need to be baselined and Tracked during the product life cycle. KPIs are focusing on Schedule, Cost/Effort, Scope/Changes | [20 empty] | R | [7 empty] | A |  |  |  | Medium | In progress
G0-3.1 | Business Plan & Marketing Strategy | Business Justification Description | [21 empty] | R | [7 empty] | A |  |  |  | High | Incomplete
G0-3.2 | Business Plan & Marketing Strategy | Marketing Strategy Established | [21 empty] | R | [7 empty] | A |  |  |  | Low/No Risk | Completed
G0-3.3 | Business Plan & Marketing Strategy | Customer Strategy Established | [21 empty] | R | [7 empty] | A |  |  |  | Medium | In progress
G0-3.4 | Business Plan & Marketing Strategy | SWOT (Strength, Weakness,Opportunities,Threat) Analysis Completed | [21 empty] | R | [7 empty] | A
G0-4.1 | Development Budget Estimate | Project complexity analysis (To be used to assess budget consistency across projects) | http://svn/rulebook/Project_Management/07_Tool_Box/ProjectComplexityMatrix.xlsx |  | A | [18 empty] | R |  | A |  | A | [7 empty] | High | Incomplete
G0-4.2 | Development Budget Estimate | Preliminary resource estimate | http://svn/rulebook/Project_Management/07_Tool_Box/ResourcePlanTemplate.xlsx |  | A | [18 empty] | R |  | A |  | A | A | A | A
G0-4.3 | Development Budget Estimate | Risks Assessment |  |  | A | [18 empty] | R |  | A |  | A
G0-4.4 | Development Budget Estimate | Initial Product Cost Estimate (Use latest Cost Model from Finance) | CostAccounting |  | A | [18 empty] | R |  | A |  | A
G0-4.5 | Development Budget Estimate | ROI (Return On Investment) estimates |  |  | A | [18 empty] | R |  | A |  | A
G0-5.1 | Feasibility Study Team | Initial team assigned for planning phase (G1) key functions to get to next gate List the new features/functions which require feasibility study until G1 | [25 empty] | R
G0-5.2 | Feasibility Study Team | Is the Project Functional Safety? if yes, assign a Functional Safety Manager in the core team, and follow the FS process SOP-29 | [25 empty] | R
G0-5.3 | Feasibility Study Team | Gate 1 target date defined (if Gate 0 approved) | [25 empty] | R
G0-5.4 | Functional Safety Team Assignment | if FuSa Project, Have the resources been assigned for the project per requirements for QM-0006 |  | C | [23 empty] | A | R |  | A
G0-6 | Gate Review Approval | Gate 0 Review Approval: - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 | FORM-0018 | [17 empty] | A |  |  | R
Note on AM4: ====== ID#AAABOlBYtsg tc={F2DA5F50-71F1-4086-95B0-E4BC1C192188} (2021-11-15 14:02:20) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk 5-Not Applicable
Note on D11: ====== ID#AAABOlRPOpA Samar Aoun (2022-06-21 14:51:34) Do we have any guideline on how to define project complexity? criterias? ------ ID#AAABOlc6l5U Lionel Federspiel (2022-09-01 20:11:38) there is the beginning of something here http://172.16.192.64/svn/data/Engineering/Planning/indieEngineeringTracker.xlsx tab Project Complexity Matrix ------ ID#AAABOlc6l5Y Lionel Federspiel (2022-09-01 20:18:02) I am taking the tab and making it a sheet to rulebook

## G0.8
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 0.8 | Category | NEW PRODUCT RFQ RESPONSE GATE |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G0.8-0 | Previous Actions | Have all actions from the previous milestone been reviewed and closed? |  |  | A | A | [17 empty] | R
G0.8-1.1 | Preliminary Product Requirements document [PPRD] | High Level (System Level ) Requirements Analysis completed | JAMA Project or Use http://svn/rulebook/toolbox template |  | A | R
G0.8-1.2 | Preliminary Product Requirements document [PPRD] | Key deliverables and feature listed |  |  | A | R
G0.8-1.3 | Preliminary Product Requirements document [PPRD] | Electrical Specifications - Critical performance criteria analyzed through feasibility studies. May lead to exploring implementation options. |  |  | A | R
G0.8-1.4 | Preliminary Product Requirements document [PPRD] | Package Family Assessed including sourcing cost -> G0.8-3.5 |  | A | A | [14 empty] | R
G0.8-1.5 | Preliminary Product Requirements document [PPRD] | Design For Manufacturing: Provide list of risks based on requirements analysis. Design For Test : Provide list of risks based on requirements analysis. |  | A | A | [6 empty] | R
G0.8-2 | IP Development plan: | Provide initial list of IP needs and a first tentative set of buy vs make. |  |  | R | A
G0.8-3.1 | Cost and Budget Analysis | Provide product development and manufacturing cost estimate as best as possible using similary complex projects to assess estimates of cost dev and use expert judgement (ask around!) | http://svn/rulebook/Project_Management/07_Tool_Box/ProjectComplexityMatrix.xlsx | [20 empty] | R
G0.8-3.2 | Cost and Budget Analysis | Provide initial Foundry Process selection with nominal mask and wafer costs (unless specific additional masks are already known, in that case ask Operation for a quote). | [21 empty] | R
G0.8-3.3 | Cost and Budget Analysis | Provide Product BOM cost estimate - If possible system level block diagram proposal. INcludes Package, leadframe, etc... |  |  | A | [14 empty] | A |  |  |  | R
G0.8-3.4 | Cost and Budget Analysis | Provide Chip Die size estimate - samed as product cost dev estimate: Use similar projects, competitor data and expert judgement. | http://svn/rulebook/Project_Management/07_Tool_Box/DieSizeEstimateTemplate.xlsx |  | R
G0.8-3.5 | Cost and Budget Analysis | Work through the Cost Model (IC, Package, tests...). Present Business Case update from G0 |  | A | A | [18 empty] | R
G0.8-3.6 | Cost and Budget Analysis | Target Supplier/Sourcing plan defined (Fab/Process, Assembly, Test House) Use FORM-0073 as template. List Risks for each suppliers (G1 ask for feasibility studies). | Quality System Doc Release Folder | A | A | [13 empty] | A | A |  |  | A | A |  |  | R | A |  | A |  | A | A
G0.8-4.1 | Project Schedule | Assess overall project schedule including number of spins expected | Initial Top Down Schedule provided by Design Engineering lead | R | A | [18 empty] | A | [5 empty] | A
G0.8-4.2 | Project Schedule | - Provide a high level resources plan that covers full product dev until G7 - Highlight specific skill set if needed - use rulebook resource template. - use smartsheet project template | http://svn/rulebook/Project_Management/07_Tool_Box/ResourcePlanTemplate.xlsx | R
G0.8-5.1 | Reliability and Quality Goals | -Reliability Assessment results for technology and for package - Reliability Engineer -Review customer user profile and specific customer reliability requirements |  | A | [13 empty] | A |  | A | R | [8 empty] | A
G0.8-5.2 | Reliability and Quality Goals | -ATE HW and SW resources required for Qual assessed/estimated cost listed -Risks related to Qual Test program readiness |  | A | [13 empty] | A | R |  | A | [8 empty] | A
G0.8-5.3 | Reliability and Quality Goals | -List the requirements related to Compliance (Standards) tests. Highlight risk and new standards. |  | A |  | R | [18 empty] | A
G0.8-6 | Production Test Flow | - Basic Test Requirements have been assessed by ATE team: - Test insertions, test temperatures and test time estimated - ATE HW and SW resources estimates (not secured) - High Level Risks related to test flow assessed - Probe card , FT load board priorities vs design and customer needs |  | A | [14 empty] | R | [10 empty] | A
G0.8-7.1 | Licenses, CAD, Tools, IT Needs | Basic assessment completed such as specific needs not covered by current infrastructure |  | R
G0.8-7.2 | DVT (and other) Test Equipment needs | Basic assessment completed such as specific needs not covered by current infrastructure |  | R
G0.8-8 | Safety Plan Activities | Have the Safety plan actvities been completed per the safety plan? (See JAMA) - See FORM-0038 for document RACSI |  | R | A | [8 empty] | A | C
G0.8-9 | Safety Audit and Assessment | Fusa Confirmation Measures: - Completed Fusa Assessment (ISO26262, depending on ASIL requirements) |  | R | A | [8 empty] | A | C
G0.8-10 | Cyber Security Plan Activities | Have the Cybersecurity plan activities been completed per the cybersecurity plan? | Refer to FORM-0038 for the list of expected work packages ( at this time, please ask Tripati for the FORM) | R | A | [10 empty] | A | C
G0.8-11 | Gate Review Approval | Gate 08 Review approval - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 | [18 empty] | A |  |  | R

## G1
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 1 | Category | PRD (PRODUCT REQUIREMENTS) AND PLANNING REVIEW GATE REVIEW |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G 1-0 | Previous Actions | Have all actions from the previous milestone been reviewed and closed? |  | R | A | A | [17 empty] | A | [14 empty] | high risk
G1-1.1 | Product Requirements document [PRD] | Detailed Project Scope defined (all customer requirements reviewed) | JAMA Project or Use http://svn/rulebook/Project_Management/07_Tool_Box |  | R | A | [14 empty] | A | A |  | A
G1-1.2 | Product Requirements document [PRD] | Key deliverables and feature list (all customer requirements reviewed) |  |  | R | A | [14 empty] | A | A |  | A
G1-1.3 | Product Requirements document [PRD] | System level requirements (all customer requirements reviewed) |  |  | R | A | A | A | [12 empty] | A | A |  | A
G1-1.4 | Product Requirements document [PRD] | Electrical Specifications (all customer requirements reviewed) |  |  | R | A | A | A | [12 empty] | A | A |  | A
G1-1.5 | Product Requirements document [PRD] | Package definition (all customer requirements reviewed) |  |  | A | [14 empty] | R | A | A |  | A
G1-1.6 | Product Requirements document [PRD] | PRD signed by customer (DocuSign or wet signature) | stored in project Management SVN folder PRD | R | A | A | [14 empty] | A | A |  | A
G1-1.7 | Product Requirements document [PRD] | Required feasibility studies results |  |  | R | A | [14 empty] | A | A |  | A
G1-1.8 | Product Requirements document [PRD] | Derivative product application assessment (future proofing) |  | A | A | A | [14 empty] | A | A |  | R | [14 empty] | high risk
G1-2.1 | IP Development plan | - Analyze optimum IP choices - Reuse Internal IP Vs Acquire External IP Vs New Custom IP development |  |  | R |  | A | A | [15 empty] | A |  |  |  | A |  |  |  | A
G1-2.2 | IP Development plan | List the new external IP needs and sourcing status. Use 3rd party IP assessment form. | refer SOP-0061 3rd Party IP Sourcing |  | R |  | A | A | [15 empty] | A |  |  |  | A |  |  |  | A
G1-2.3 | IP Development plan | Review of lessons learned from previous projects. SOP-0101 | Confluence Lessons Learned Corner |  | R |  | A | A | A | [14 empty] | A |  |  |  | A |  |  |  | A | [6 empty] | medium risk
G1-3 | Benchmark Analysis | Benchmark similar products in market comparing relevant technical features. Highlighting advantages and shortfalls |  |  | A | A | [17 empty] | R | [14 empty] | low risk
G1-4.1 | Cost and Budget Analysis | Full resource (update from G0) and material cost estimate completed |  | R | A | [20 empty] | A | A |  |  | A
G1-4.2 | Cost and Budget Analysis | Process choice, Device List, Mask Layers , Options. |  | R | A | [20 empty] | A | A |  |  | A
G1-4.3 | Cost and Budget Analysis | Product BOM estimate |  | A | A | [18 empty] | R |  | A | A
G1-4.4 | Cost and Budget Analysis | Product Die size estimate updated from G0/G0.8 |  | R | A | [20 empty] | A | A
G1-4.5 | Cost and Budget Analysis | DFT and DFM assessments | Assess testability and manufacturability if the design wrt requirements. Consider special characteristics. | R | A |  |  |  |  | A | [15 empty] | A | A |  |  | A
G1-4.6 | Cost and Budget Analysis | Updated Cost Model (IC, Package, tests...), ROI updated from G0/G0.8 |  | A | A | [18 empty] | R |  | A | A |  |  | A
G1-4.7 | Cost and Budget Analysis | Supplier/sourcing plan updated Feasibility agreement with each of the identified suppliers defined. | Update FORM-0073 from G0/G0.8 | A | A | [13 empty] | A | A |  |  | A | A |  |  | R | A |  | A |  | A | A
G1-5.1 | Project Schedule | Project risks listed and Initial DFMEA (AIAG/VDA and customer specific requirements compliant) |  | R | A | [21 empty] | A | [11 empty] | not applicable
G1-5.2 | Project Schedule | Update (from G0/G0.8) and publish project schedule (Smarsheet reference). - Use smartsheet project template: IC Gantt Chart Template - Bottom up Analysis from Chip Lead and Program Manager | https://app.smartsheet.com/sheets/PvmMvhRxGxg7cRVpv8FW54gv7H24r35JH86gpxW1 | R | A | A | A | A | A |  | A | A |  |  | A |  |  | A | A |  |  |  |  | A |  |  | A | [11 empty] | not applicable
G1-5.3 | Project Schedule | Resource assignment completed to support next Milestone |  | R | A | [21 empty] | A
G1-5.4 | Project Schedule | Project Org Chart created |  | R | A | [21 empty] | A
G1-5.6 | Project Schedule | From G0-2 Critical Success Factors, List Project KPIs. KPIs are focusing on Schedule, Cost/Effort, Scope/Changes | SOP-0054 | R | A | [21 empty] | A
G1-5.7 | Project Schedule | - Preliminary listing of Special product and process characteristics |  | R | A | [21 empty] | A
G1-6.1 | Reliability and Quality Goals | Reliability Assessment results for Foundry technology and 3rd Party IP |  | A | A | [7 empty] | R |  |  |  |  | A |  |  | A |  | A | [6 empty] | A
G1-6.2 | Reliability and Quality Goals | Reliability Assessment results for package |  | A | A | [12 empty] | A |  | R | A |  | A | [6 empty] | A
G1-6.3 | Reliability and Quality Goals | - Review customer user profile and specific reliability requirements - PQE - Qualification plan defined (high level) PQE |  | A | A | [12 empty] | A | A |  | R |  | A | [6 empty] | A
G1-6.4 | Reliability and Quality Goals | -List the requirements related to Compliance (Standards) tests - PE |  | A | A | [12 empty] | R | A |  | A |  | A | [6 empty] | A
G1-7.1 | Production Test Flow | -Test Requirements assessed -Test insertions, test temperatures and test time estimated -Risks related to test features, test time and coverage assessed, mitigation plan defined |  | A | [13 empty] | A | R |  | A | [8 empty] | A
G1-7.2 | Production Test Flow | ATE HW and SW resources required assessed/listed (including probing) |  | A | A | [12 empty] | A | R |  | A |  | A | [6 empty] | A
G1-8.1 | System Integration, Field Test Plan | Preliminary plan created – Risk assessment |  | A | R
G1-8.2 | System Integration, Field Test Plan | Compliance Test suite defined |  | A | R
G1-9.1 | Infrastructure Needs | Licenses, CAD, Tools, IT Needs Refer to G1_IT_CAD_Checklist: Specific tools requirements, servers, Contractor needs, PDKs | http://svn/rulebook/Project_Management/01_Gate_Reviews/G1/02_Checklists/G1_IT_CAD_Checklist.xlsx | A | R | [22 empty] | A |  | A
G1-9.2 | Infrastructure Needs | DVT (and other) Test Equipment needs Refer to G1_DVT_Equip_Checlist.xls | http://svn/rulebook/Project_Management/01_Gate_Reviews/G1/02_Checklists/G1_DVT_SVT_Equip_Checklist.xlsx | A | A | A |  |  |  |  | R | [16 empty] | A
G1-10.1 | Project Management | Customer Alignment and approval of Project Execution plan |  | A | R
G1-10.2 | Project Management | Review all JIRA tickets. |  | A | R
G1-10.3 | Project Management | Part number creation request (Refer to SOP-0022) |  | A | [19 empty] | R
G1-11 | FuSa Safety Plan Activities Completed Per Safety plan | Fulfillment of the G1 milestone deliverables according to the Safety plan including Configuration Management update and approval (in Jama) |  | R | A | [8 empty] | A
G1-12 | FusA Confirmation Measures | Completed Fusa Assessment (ISO26262, depending on ASIL requirements) |  | A | A | [8 empty] | R
G1-13 | Cyber Security Plan Activities | Have the Cybersecurity plan activities been completed per the cybersecurity plan? | Refer to FORM-0038 for the list of expected work packages ( at this time, please ask Tripati for the FORM) | R | A | [10 empty] | A | C
G1-14 | Gate Review Approval | Gate 1 Review approval - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 |  | R | [16 empty] | A
Note on AM4: ====== ID#AAABOlc7NUs tc={B422D12E-9674-4BDC-BA3D-5F4C6BE70047} (2021-11-15 14:23:55) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk
Note on D8: ====== ID#AAABOlc7NUo Samar Aoun (2022-06-21 14:53:22) can we put instead: System Level requirements: - Reviewed and Approved
Note on D27: ====== ID#AAABOlRPOo4 Lionel Federspiel (2022-09-01 22:00:26) Need a booking method
Note on F44: ====== ID#AAABOlBYtsk Lionel Federspiel (2022-10-07 20:04:06) @kyle.fabris@indiesemi.com Why is the PGM Responsible of delivering the FuSa Safety Plan? _Assigned to Kyle Fabris_

## G2
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 2 | Category | ARCHITECTURE REVIEW GATE REVIEW |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G2-0 | Previous Actions | Have all actions from the previous milestone been reviewed and closed? |  | R | A
G2-1.1 | Chipset partitioning | Functional ASIC partitioning: Analog & Digital Partitioning, HW/FW |  | A | R | A | A | A
G2-1.2 | Chipset partitioning | System I/O, Major On-Chip / Off-chip Interfaces defined |  | A | R | A | A | A
G2-1.3 | Chipset partitioning | Clock and Reset Strategy defined |  | A | R | A | A | A
G2-1.4 | Chipset partitioning | Power management Concept defined |  | A | R | A | A | A
G2-2.1 | System Architecture Review | High level Architecture is broken down at a level it can be handed over to circuit designers. THis is not a schematic complete stage. |  | A | R | A | A | A
G2-2.2 | System Architecture Review | Features alignment with PRD (Are the Stakeholders requirements reviewed and breakdown to system and block requirements completed, in status " reviewed" in the requirement management system?) |  | A | R | A | A | A
G2-2.3 | System Architecture Review | Internal & External (3rd party) IP choice is made. Provide IP sourcing status. | Follow SOP-0061 and Fill FORM-0086 (Analog IP) and FORM-0088 (Digital IP) | A | R | A | A | A
G2-2.4 | System Architecture Review | ESD strategy - Provide concept diagram with primary and secondary ESD clamps. |  | A | R | A | A | A
G2-2.5 | System Architecture Review | initial Block level Design Reviews Planned for designers to take broken down requirments and start IP dev. |  | A | R | A | A | A | A |  | A
G2-2.6 | System Architecture Review | DFMEA update (AIAG/VDA and customer specific requirements compliant) | Medini Database | A | R | A | A | A | A |  | A
G2-3.1 | Design and Verification | Chip Level verification plan defined - focus on requirement driven verification methodology |  | A | A | A | A | A | R
G2-3.2 | Design and Verification | Spec Compliance Matrix generated - to be used for design and verification reviews. | https://docs.google.com/spreadsheets/d/1gBVeYQBWrJU1KeHPKE9YJHGwNqDgkesu/edit?usp=share_link&ouid=112830870575640631435&rtpof=true&sd=true | A | R | A | A | A | A
G2-4 | Design for Test and Design for Manufacturability Review | - DFT & DFM features and plan - Review Targeted process technology (PF, CP , PFMEA) - Present chip level test approach subdivided to the IP level - Should cover digital tests (SCAN, MBIST) and analog tests (BIST, test bus, fault injection, etc.) | ref: QM-0060 PMFEA: Foundry, check that Supplier Quality (SQA) has PFMEA records. Package: check with Package Engineer | A | R | A |  |  |  | A | A | A | A |  |  |  |  | A | A |  | A | [8 empty] | A
G2-5.1 | Project Management | Project Schedule Update (smarsheet) | update project schedule from G1 and highlight changes and impacts | R | A | A | [11 empty] | A | A |  |  |  |  | A | [5 empty] | A
G2-5.2 | Project Management | Die area estimate AND Product costs update | Update BOM Cost | A | A | A | [17 empty] | R
G2-5.3 | Project Management | Product Cost Model update | Make sure cost model used is accurate - Check with Finance. | R | A | A | [11 empty] | A | A |  |  |  |  | A | [5 empty] | A
G2-5.4 | Project Management | Project cost and business case update | ROI/NPV | R | A | A | [11 empty] | A | A |  |  |  |  | A | [5 empty] | A
G2-5.5 | Project Management | Resource plan Update | update resource plan with name allocation as much as possible. Identify gaps. | R | A | A | [11 empty] | A | A |  |  |  |  | A | [5 empty] | A
G2-5.6 | Project Management | Project Organisation chart Update | if applicable | R | A | A | [11 empty] | A | A |  |  |  |  | A | [5 empty] | A
G2-5.7 | Project Management | Project risks Update | Highlight chnages in project risks if any. | R | A | A | [11 empty] | A | A |  |  |  |  | A | [5 empty] | A
G2-5.8 | Project Management | Supplier/sourcing plan updated. At this point the plan should be fairly mature especialy wrt foundry and assembly house. | update FORM-0073 from G1 | A | A | [13 empty] | A | A |  |  | A | A |  |  | R | A |  | A |  | A | A
G2-5.9 | Project Management | Review JIRA tickets and make sure they are all properly classified |  | R | A | A | [17 empty] | A
G2-5.10 | Project Management | Review Patent idea and decide on filing |  | R | A | [16 empty] | A
G2-6 | Fusa Safety Plan | Fulfillment of the G2 milestone deliverables according to the Safety plan including Configuration Management update and approval (in Jama) |  | R | [9 empty] | A
G2-7 | Fusa Confirmation Measures | Completed Fusa Assessment (ISO26262, depending on ASIL requirements) |  | A | [9 empty] | R
G2-8 | Cyber Security Plan Activities | Have the Cybersecurity plan activities been completed per the cybersecurity plan? | Refer to FORM-0038 for the list of expected work packages ( at this time, please ask Tripati for the FORM) | R | A | [10 empty] | A | C
G2-9 | Gate Review Approval | Gate 2 Review Approval: - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 |  | R | [16 empty] | A
Note on AM4: ====== ID#AAABOlc6l5c tc={59FD51DB-5B07-4BBF-A27F-62019C8DF522} (2021-11-15 14:23:56) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk

## G3
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 3 | Category | Tape Out Gate Review |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G3-0 | Previous Actions | Have all actions from the previous milestone been reviewed and closed? |  | R | A
G3-1.1 | Specification | All internal design implementation specifications are updated or have a plan to be updated in sphinx. External spec relevant to the usage of the product should also be ported to sphin format unless they are delivered as is to customers. |  | A | R | A | A | A | A
G3-1.2 | Specification | Register map released | Sphinx reg Map (auto generated) | A | R | A | A | A | A
G3-1.3 | Specification | List major changes made to the architecture design since G2 was completed. | The idea here is to ask if the system Architecture Changed since G2 (If major changes made, must be supported by change request form). | A | R | A | A | A | A | A | A | A
G3-2.1 | Tape Out Design and Verification Checks | IC Development Checklist updated, reviewed and signed off by key stake holders (include analog and digital test plan review, test run results/report review, signoff over PVT and MC) | FORM-0087 | A | R | A | A | A | A | A
G3-2.2 | Tape Out Design and Verification Checks | Spec compliance matrix (SCM) Updated - If not document plan to complete the update and review SCM against PRD (Requirements) and Datasheet (if available). | see G2-3.2 for template | A | R | A | A | A | A
G3-3.1 | Tape Out Design and Verification Checks | Tape Out Checklist documented and formally reviewed. | FORM-0059 | A | R | A | A | A | A
G3-4.1 | DVT Test Plan | Test plans initiated documented before Engineering samples are available. List FW code needs for DVT if any. Review equipment list from G1. |  | A | A | A |  |  |  |  | R
G3-4.2 | DVT Test Plan | Hardware development plan (breakout boards, application boards) |  | A | A | A |  |  |  |  | R
G3-5.1 | System Test Plan | System test Plan and FW support needs list |  | A | A | A | [5 empty] | R
G3-5.2 | System Test Plan | Hardware development plan (breakout boards, application boards) |  | A | A | A | [5 empty] | R
G3-6.1 | Design For test and Manufacturing | DFT & DFM coverage reviewed |  | A | A | A |  |  |  | A | A | [6 empty] | A | R | [10 empty] | A
G3-6.2 | Design For test and Manufacturing | ATE Test plan assessment (risk) |  | A | A | A |  |  |  |  | A | [6 empty] | A | R | [10 empty] | A
G3-6.3 | Design For test and Manufacturing | Test platform decision/choice confirmed |  | A | A | A |  |  |  |  | A | [6 empty] | A | R | [10 empty] | A
G3-6.4 | Design For test and Manufacturing | Plan for both Final Test Load board (with handler) and Probe Card development. |  | A | A | A |  |  |  |  | A | [6 empty] | A | R | [10 empty] | A
G3-6.5 | Design For test and Manufacturing | Design Analysis to extract a Target Yield based on Foundry D0, digital contents, etc... |  | A | A | A |  |  |  |  | A | [6 empty] | R | A | [10 empty] | A
G3-7 | Design FMEA | Design FMEA update: Identify potential design risks, mitigation (AIAG/VDA and customer specific requirements compliant) |  | A | R | A |  |  |  |  | A |  |  | A |  |  |  | A | A |  | A | [8 empty] | A
G3-8 | Qualification and Reliability test plan | Initial Qualification test conditions & planning defined (AEC, JEDEC, customer specific requirements compliant) including stress lab and Test locations for qualification execution. Definition and preparation of Qualification HW & SW requirements with CL and PE (HTOL, THB and LU stress boards) |  | A | A | [12 empty] | A |  |  | R | [8 empty] | A
G3-9.1 | Product Manufacturing Development | Supplier/sourcing plan FINALIZED | FORM-0073 updated from G2 | A | A | [13 empty] | A | A |  |  | A | A |  |  | R | A |  | A |  | A | A
G3-9.2 | Product Manufacturing Development | Initial Qualification test conditions & planning defined (AEC, JEDEC, customer specific requirements compliant) including stress lab and Test locations for qualification execution |  | A | A | [12 empty] | A |  | R | A | [8 empty] | A
G3-9.3 | Product Manufacturing Development | Definition and preparation of Qualification HW & SW requirements with CL and PE (HTOL, THB and LU stress boards) | FORM-0074 | A | A | [12 empty] | R |  |  | A | [8 empty] | A
G3-9.4 | Product Manufacturing Development | Review Prototype Build Process Flow & Control Plan |  | A | A | [12 empty] | R |  |  | A | [8 empty] | A
G3-9.5 | Product Manufacturing Development | Review Special product & Process characteristics |  | A | A | [12 empty] | R |  |  | A | [8 empty] | A
G3-9.6 | Product Manufacturing Development | Confirm manufacturing and assembly cycle time |  | A | A | [12 empty] | R |  |  | A | [8 empty] | A
G3-9.7 | Product Manufacturing Development | Target Yield for production defined (Baseline) |  | A | A | [12 empty] | R |  |  | A | [8 empty] | A
G3-10.1 | Project Management | Update on Project schedule (including engineering lot manufacturing and assembly cycle time) |  | R | A | [12 empty] | A |  |  |  | A | [7 empty] | A
G3-10.2 | Project Management | Update Resource plan |  | R | A | [12 empty] | A | A |  |  | A | [7 empty] | A
G3-10.3 | Project Management | Update on Die size and other work products affecting cost. | Highlight design features changes if any justifying the die size or BOM cost change. | A | R | [16 empty] | A |  | A
G3-10.4 | Project Management | Update cost model and business case | http://172.16.192.64/svn/data/Admin/Financial/NPI%20Business%20Case%20Analysis/NPI%20Business%20Case%20Analysis%20Q3%2721.xlsx | A | A | [12 empty] | A | A |  |  | A |  | R | [5 empty] | A
G3-10.5 | Project Management | Plan Lessons Learned post Tape out - The documentation shall be recorded in Confluence | Create Confluence page - see http://confluence.indiesemi.com:8090/x/MydNBw | R | A | [16 empty] | A
G3-10.6 | Project Management | Wafer and parts sampling plan (prototype) | Sampling plan can be put in smartsheet sample order https://app.smartsheet.com/sheets/9G8QJjVh2VQc2P7HvWHHqCF5jW843VQww3MGQq71 | R | [13 empty] | A |  |  |  | A |  | A | [5 empty] | A
G3-10.7 | Project Management | All JIRA tickets reviewed and classified properly |  | R | A | [16 empty] | A
G3-11 | Fusa Safety Plan | Fulfillment of the G3 milestone deliverables according to the Safety plan including Configuration Management update and approval (in Jama) |  | R | A | [8 empty] | A
G3-12 | Fusa Confirmation Measures | Completed Fusa Assessment (ISO26262, depending on ASIL requirements) |  | A | A | [8 empty] | R
G3-13 | Cyber Security Plan Activities | Have the Cybersecurity plan activities been completed per the cybersecurity plan? | Refer to FORM-0038 for the list of expected work packages ( at this time, please ask Tripati for the FORM) | R | A | [10 empty] | A | C
G3-14 | Gate Review Approval | Gate 3 Review Approval: - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 |  | R | [16 empty] | A
G3-15 | Customer Approval | Customer approval for tape out (if applicable) (Cloud JIRA Ticket with customer approval) |  | R | [19 empty] | A
Note on AM4: ====== ID#AAABOlc6l5k tc={9B7191BC-B423-4F57-8EAE-33D1652BB068} (2021-11-15 14:23:55) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk
Note on E6: ====== ID#AAABOlRPOow Lionel Federspiel (2022-09-01 23:39:10) we need to specify when datasheet must be released from internal spec.
Note on E8: ====== ID#AAABOlc7NU4 Lionel Federspiel (2022-09-01 23:17:07) I wonder what that is ?!?

## G4
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 4 | Category | DVT Gate Review |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G4-0 | Previous Actions | Have all actions from the previous milestone been reviewed and closed? |  | R | A
G4-1.1 | DVT Test Results Review | Validation data, Block level testing and characterization across VT |  | A | A | A |  |  |  |  | R | [7 empty] | A
G4-1.2 | DVT Test Results Review | Spec Compliance Matrix update | see G2-3.2 for template | A | R | A |  |  |  |  | A | [6 empty] | A | A
G4-1.3 | DVT Test Results Review | Failure to meet spec clearly listed with a plan to waive or fix on the next revision, SW workarounds listed |  | A | R | A |  |  |  |  | A | [7 empty] | A
G4-1.4 | DVT Test Results Review | Trim Codes/Calibration procedures documented (Flash map) |  | A | R | A |  |  |  |  | A | [7 empty] | A
G4-1.5 | DVT Test Results Review | Bug List generated with FIX (JIRA) – SW workarounds |  | A | R | A |  |  |  |  | A | [7 empty] | A
G4-1.6 | DVT Test Results Review | Reference documents update to reflect test data results: - Datasheet Electrical Spec (Change Request Needed) - Non compliance Notification, waiversc Notifications - Errata Sheet - Application notes |  | A | R | A | [11 empty] | A | A | [5 empty] | A
G4-2 | ATE Test Result Review | ATE data of initial builds and mini-split characterization review in addition to DVT data for design recentering based on preliminary process variation data from foundry, assembly, and ATE test |  | A | A | A | A | A |  |  | A | [6 empty] | A | R |  | A | [8 empty] | A
G4-3.1 | ATE Test Plan | ATE Test Plan: HW Definition (Load Board), Handler and Tester configuration completed |  | A | A | [13 empty] | R | [10 empty] | A
G4-3.2 | ATE Test Plan | ATE Test Plan - Calibration procedures implemented |  | A | A | [13 empty] | R | [10 empty] | A
G4-3.3 | ATE Test Plan | ATE Test Plan - ATE test plan generated |  | A | A | [13 empty] | R | [10 empty] | A
G4-4.1 | Pre-Qualification Data assessment | ESD & LU results |  | A | A | [12 empty] | R |  |  | A
G4-4.2 | Pre-Qualification Data assessment | HTOL results |  | A | A | [12 empty] | R |  |  | A
G4-4.3 | Pre-Qualification Data assessment | Package stress results |  | A | A | [12 empty] | R |  |  | A
G4-4.4 | Pre-Qualification Data assessment | EMI/EMC results |  | A | A | [12 empty] | R |  |  | A
G4-4.5 | Pre-Qualification Data assessment | Electrical Distribution (Pre-characterization) results |  | A | A | [12 empty] | R |  |  | A
G4-4.6 | Pre-Qualification Data assessment | Qualification test plan update (AEC, JEDEC, customer specific requirements compliant) |  | A | A | [12 empty] | A |  |  | R
G4-5.1 | Project Management | Review all Jira tickets |  | R | A | [5 empty] | A | [6 empty] | A | A
G4-5.2 | Project Management | Review Project schedule |  | R | A | [5 empty] | A | [6 empty] | A | A
G4-5.3 | Project Management | Review Resource Plan |  | R | A | [5 empty] | A | [6 empty] | A | A
G4-5.4 | Project Management | Update cost model, business case (ROI) as needed |  | A | [19 empty] | R
G4-5.5 | Project Management | DFMEA update from DVT and ATE Test Results - Updated from DVT results (AIAG/VDA and customer specific requirements compliant) |  | A | R | A |  |  |  |  | A | [6 empty] | A |  |  |  | A
G4-6 | Fusa Safety Plan | Fulfillment of the G4 milestone deliverables according to the Safety plan including Configuration Management update and approval (in Jama) |  | R | A | [8 empty] | A
G4-7 | Fusa Confirmation Measures | Completed Fusa Assessment (ISO26262, depending on ASIL requirements) |  | A | A | [8 empty] | R
G4-8 | Cyber Security Plan Activities | Have the Cybersecurity plan activities been completed per the cybersecurity plan? | Refer to FORM-0038 for the list of expected work packages ( at this time, please ask Tripati for the FORM) | R | A | [10 empty] | A | C
G4-9 | Gate Review Approval | Gate 4 Review approval: - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 |  | R | [16 empty] | A
Note on AM4: ====== ID#AAABOlc7NUw tc={281AAAAD-1356-458B-8B0E-D443F5FDF867} (2021-11-15 14:23:56) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk
Note on E15: ====== ID#AAABOlc7NU0 Lionel Federspiel (2022-09-02 00:06:09) where is defined when the various ATE Programs (probe, FT, charact, HTOL, etc....) are defined, implemented and released?
Note on C16: ====== ID#AAABOlc7NU8 Lionel Federspiel (2022-10-07 20:11:57) @samar.aoun@indiesemi.com who owns this now?

## G5
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 5 | Category | System Validation Gate Review |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G5-0 | Previous Actions | Have all actions from the previous milestone been reviewed and closed? |  | R | A
G5-1 | System Integration & Interface validation | End to end bench performance validation in all use cases, Results feedback. |  |  | A | [5 empty] | R
G5-2.1 | Field test / Platform Test Results | Field test / Platform Test Results: - Field test, Key performance validation in different use case scenarios |  |  | A | [5 empty] | R
G5-2.2 | Field test / Platform Test Results | Field test / Platform Test Results: - Detailed performance review |  |  | A | [5 empty] | R
G5-2.3 | Field test / Platform Test Results | Field test / Platform Test Results: - Potential shortfalls, areas of improvement |  |  | A | [5 empty] | R
G5-2.4 | Field test / Platform Test Results | Field test / Platform Test Results: - Final product with chipset mounted on end platform |  |  | A | [5 empty] | R
G5-2.5 | Field test / Platform Test Results | Field test / Platform Test Results: - Field tests are performed to ensure compliance to product performance |  |  | A | [5 empty] | R
G5-2.6 | Field test / Platform Test Results | Field test / Platform Test Results: - List of compliance and shortfalls is prepared |  |  | A | [5 empty] | R
G5-3 | Specification | Updates to internal Product Specification and datasheet |  | A | R | [19 empty] | A
G5-4.1 | ATE Test | ATE test program released to production site (Gage R&R performed at indie and at supplier and pass) |  |  | A | [12 empty] | A | R | [10 empty] | A
G5-4.2 | ATE Test | ATE test program for Qualification released to Test site |  |  | A | [12 empty] | A | R | [10 empty] | A
G5-4.3 | ATE Test | Bench To Test Correlation Review completed |  |  | A | [12 empty] | A | R | [10 empty] | A
G5-4.4 | ATE Test | Spec Compliance Matrix release in svn | see G2-3.2 for template |  | A | [12 empty] | A | R | [10 empty] | A
G5-5.1 | PPAP | PPAP package received from all subcontractors |  | A | [13 empty] | A | A |  | A |  | R | [6 empty] | A
G5-5.2 | PPAP | PPAP reviewed and PSW signed and returned to subcontractors by indie |  | A | [13 empty] | A | A |  | A |  | R | [6 empty] | A
G5-5.3 | PPAP | Upcoming Supplier Engineering Change Review |  | A | [13 empty] | A | A |  | A |  | R | [6 empty] | A
G5-6.1 | Final Qualification and Characterization | Qualification samples tested, Qualification HW ready to start final qualification. |  | A | [13 empty] | R |  |  | A
G5-6.2 | Final Qualification and Characterization | Characterization samples received, including corner lots |  | A | [13 empty] | R |  |  | A
G5-6.3 | Final Qualification and Characterization | Qual build report received from assembly house, and reviewed |  | A | [13 empty] | R |  |  | A
G5-6.4 | Final Qualification and Characterization | Define Safe Launch Plan with PQE and SQE |  | A | [13 empty] | R |  |  | A
G5-7 | Sampling | Pre-production sampling (NPI Admin) Transfer responsibility from NPI administrator to operations
G5.8 | Failure Analysis Flow | Product Failure Analysis work instruction released. according to SOP-0016 | [19 empty] | R
G5-9.1 | Project Management | Agreement on performance adequacy, Essential, Desirable fixes in the next revision (if required) |  | A | R | [12 empty] | A | [9 empty] | A
G5-9.2 | Project Management | Review all JIRA tickets and update |  | A | R | [12 empty] | A | [9 empty] | A
G5-9.3 | Project Management | Review Project schedule |  | A | R | [12 empty] | A | [9 empty] | A
G5-9.4 | Project Management | Review resource plan |  | A | R | [12 empty] | A | [9 empty] | A
G5-9.5 | Project Management | Review DFMEA
G5-9.6 | Project Management | Cost Model and ROI update |  | A | A | [12 empty] | A | [5 empty] | R |  |  |  | A
G5-10 | Fusa Safety Plan | Fulfillment of the G5 milestone deliverables according to the Safety plan including Configuration Management update and approval (in Jama) |  | R | A | [8 empty] | A
G5-11 | Fusa Confirmation Measures | Completed Fusa Assessment (ISO26262, depending on ASIL requirements) |  | A | A | [8 empty] | R
G5-12 | Cyber Security Plan Activities | Have the Cybersecurity plan activities been completed per the cybersecurity plan? | Refer to FORM-0038 for the list of expected work packages ( at this time, please ask Tripati for the FORM) | R | A | [10 empty] | A | C
G5-13 | Gate Review Approval | Gate 5 Review Approval: - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 |  | R | [16 empty] | A
Note on AM4: ====== ID#AAABOlRPOo0 tc={CF87A86A-A967-487A-9150-1CEF7604D9F8} (2021-11-15 14:23:56) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk
Note on D25: ====== ID#AAABOlc7NVA Lionel Federspiel (2022-10-07 20:13:27) who added this? missing owner
Note on E25: ====== ID#AAABOlc7NVE Lionel Federspiel (2022-09-02 00:15:07) who is NPI admin? ------ ID#AAABOlc7NVI Samar Aoun (2022-09-02 16:27:00) Mary Kolanda

## G6
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 6 | Category | PPAP Gate Review |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G6-0 | Previous Actions | Have all actions from the previous milestone been reviewed and closed? |  | R | A
G6-1.1 | Device Qualification Test Results Review | Operating life test (HTOL, HAST), ELFR |  | A | A | [12 empty] | R
G6-1.2 | Device Qualification Test Results Review | ESD & Latchup |  | A | A | [12 empty] | R
G6-1.3 | Device Qualification Test Results Review | Package qual, package integrity |  | A | A | [12 empty] | R
G6-1.4 | Device Qualification Test Results Review | Qualification test report (AEC, JEDEC, customer specific requirements compliant) |  | A | A | [12 empty] | A |  |  | R
G6-1.5 | Device Qualification Test Results Review | Bench to Test correlation |  | A | A | [5 empty] | A | [6 empty] | R | A
G6-1.6 | Device Qualification Test Results Review | Characterization report |  | A | A | [5 empty] | A | [6 empty] | R | A | [10 empty] | A
G6-1.7 | Device Qualification Test Results Review | -Yield status (for each test insertion in probing and FT). - Yield target set |  | A | A | [12 empty] | R | A |  |  |  |  | A | [5 empty] | A
G6-1.8 | Device Qualification Test Results Review | Safe Launch Plan release with PQE and SQE |  | A | A | [12 empty] | R | A | [10 empty] | A
G6-2 | Device Qualification Test Results Review | EMI/EMC compliance tests if required |  | A | A | [12 empty] | R | [6 empty] | A |  |  |  |  | A
G6-3.1 | Production Readiness | Wafer Acceptance Criteria reviewed with/accepted by the foundry |  | A | A | [12 empty] | A | A |  |  | A | A |  |  |  | R
G6-3.2 | Production Readiness | Finalizing and freezing all Control Plans / Process Flow (wafer fab, Assembly and test) |  | A | A | [12 empty] | A | A |  |  | A | A |  |  |  | R
G6-4 | Characterization and Yield review | Split lot Characterization results completed and analyzed |  | A | A | [12 empty] | R | A
G6-5.1 | ATE Test | Preliminary Yield Assessment Made and Yield Target defined |  | A | A | [12 empty] | A | R | [10 empty] | A
G6-5.2 | ATE Test | FT program (Product Functional Screen Criteria Set ) ready for production release |  | A | A | [12 empty] | A | R | [10 empty] | A
G6-5.3 | ATE Test | Load board(s) transfer to test site ready |  | A | A | [12 empty] | A | R | [10 empty] | A
G6-5.4 | ATE Test | Probing Test program transfer to test site |  | A | A | [12 empty] | A | R | [10 empty] | A
G6-5.6 | ATE Test | Volume test capacity secured to meet volume ramp |  | A | A | [12 empty] | A | R | [10 empty] | A
G6-6.1 | PPAP | PPAP package Delivery to Customer ready-ness. List status per items. | A key goal of G6 is to review that the status of the PPAP workpackages so we can with confidence close this gate. Any open point should be list as open action with due dates. | A | A | [12 empty] | A |  |  |  | R |  | A
G6-6.2 | PPAP | PPAP approval received from customer (signed PSW or customer specific approval method) Customer approval task must be completed before any production shipments. Production shipments requested by the customer prior to receipt of the signed PSW (or equivalent) requires a waiver from the customer to allow shipment without PPAP approval. | This check point shall happen after G6 is approved. Create a JIRA ticket as Action Plan. | A | A | [12 empty] | A |  |  |  | R |  | A
G6-7.1 | Project Management | Review and close all JIRA tickets |  | R | A | [12 empty] | A |  |  | A |  |  | A
G6-7.2 | Project Management | Plan Lessons learned with the project core team members. Use Confluence page created at G3 | Lessons Learned Corner | R | A | [12 empty] | A |  |  | A |  |  | A
G6-7.3 | Project Management | Review DFMEA, ensure all actions are closed and risks re-assessed |  | R | A | [12 empty] | A |  |  | A |  |  | A
G6-7.4 | Project Management | Review Patent idea and decide on filing |  | R | A | [12 empty] | A |  |  | A |  |  | A
G6-7.5 | Project Management | Update Cost Model and ROI |  | A | A | [12 empty] | A |  |  | A |  |  | R
G6-8 | Fusa Safety Plan | Fulfillment of the G6 milestone deliverables according to the Safety plan including Configuration Management update and approval (in Jama) |  | R | A | [8 empty] | A
G6-9 | Fusa Confirmation Measures | Completed Fusa Assessment (ISO26262, depending on ASIL requirements) |  | A | A | [8 empty] | R
G6-10 | Cyber Security Plan Activities | Have the Cybersecurity plan activities been completed per the cybersecurity plan? | Refer to FORM-0038 for the list of expected work packages ( at this time, please ask Tripati for the FORM) | R | A | [10 empty] | A | C
G6-11 | Gate Review Approval | PPAP Gate Review Approval: - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - Required approvals list from SOP007 - Docusign. |  | R | [16 empty] | A
Note on AM4: ====== ID#AAABOlc6l5g tc={6C40097C-FA2E-479F-BB6F-2EDDC086AD49} (2021-11-15 14:23:55) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk

## G7
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 7 | Category | Start of Production Gate Review |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G7-0 | Previous Actions | Have all actions from the previous milestone been reviewed and closed? |  | R | A
G7-1.1 | Safe Launch Report | Safe Launch data collected and assessed |  | A | A | [12 empty] | R | A |  | A |  | A | [6 empty] | A
G7-1.2 | Safe Launch Report | Burn in and reliability data assessed and pass |  | A | A | [12 empty] | R | A |  | A |  | A | [6 empty] | A
G7-1.3 | Safe Launch Report | Yield target reviewed and continuous improvement plan defined |  | A | A | [12 empty] | R | A |  | A |  | A | A | [5 empty] | A
G7-2.1 | Safe Launch Exit | Present Lessons Learned to management | Lessons Learned Corner | R | A | [8 empty] | A |  |  |  | A | A |  |  | A | [5 empty] | A |  | A
G7-2.2 | Safe Launch Exit | Customer approval for safe launch exit | [15 empty] | R |  |  |  | A
G7-3 | Gate Review Approval | Gate 7 Review Approval: - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 | [15 empty] | R
Note on AM4: ====== ID#AAABOlRPOo8 tc={D10EECE1-3F80-4A91-88FC-94C0CB1E5F08} (2021-11-15 14:23:55) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk

## G8
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 8 | Category | End Of Life Gate Review |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G8-1.1 | Customer Notification | Send PCN notification to customer (SOP-0006 EOL notice) | [15 empty] | A |  |  |  | A |  | R | [5 empty] | A
G8-1.2 | Customer Notification | Receive customer feedback | [15 empty] | A |  |  |  | A |  | R | [5 empty] | A
G8-2.1 | Orders | Plan delivery according to customer feedback | [15 empty] | A | [8 empty] | R |  |  | A
G8-2.2 | Orders | Manage stock | [15 empty] | A | [8 empty] | R |  |  | A
G8-3 | Product Data Record | Follow indie product data archiving requirements (SOP-0004 Control of Documented information) | [15 empty] | R
G8-4 | Gate Review Approval | Gate 8 Review Approval: - Attendees: please fill in <Project Gate Planning sheet> - Gate review result: Approved/Approved with actions/Rejected. - Action Items: <link> (JIRA) (Use a label Gx to make your life easier…) - People/Function Required for approvals listed in SOP-0007 -> then Docusign. - People/function that should attend the review listed in SOP-0007 | [15 empty] | R |  |  | A
Note on AM4: ====== ID#AAABOlc7NVM tc={8DD592E7-7EF3-4857-BD9E-0AFC858F56B2} (2021-11-15 14:23:55) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk

## G9
| FORM-0003 Rev 6.0 |  |  | CORE TEAM MEMBERS | [23 empty] | Management
|  |  |  | PO | Design Engineering | [8 empty] | FuSa |  | CySe |  | PETE |  | Package | QA |  |  | Sales & Marketing |  | Finance | OPS
Gate # | Category | Task | Template - Guidelines | Program Manager | Chip Lead | System Architect | Analog Lead | Digital Lead | Verification Lead | DFT Lead | DVT Lead | System Test Lead | Reliability Engineer | FuSa Manager | FuSa Enginer | CySe Manager | CySe Engineer | Product Engineer | ATE Test Engineer | Package Engineer | Product Quality Eng. | Customer Quality | Supplier Quality | Product Manager | Application Eng. | Finance Manager | Operation Manager | VP Eng. (CE/BU) | FuSa CySe Director | VP Prdct and Test | VP Quality | BU GM | Operations Director | Results | Link(s) to evidence(s) | Risk | Status (wrt the gate review) | Actions #
Gate 9 | Category | Test Gate |  | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | <name> | Results | Link(s) to Evidence(s) |  | Status | Actions #
G8-1.1 | Customer Notification | Send PCN notification to customer (SOP-0006 EOL notice) | [15 empty] | A |  |  |  | A |  | R | [5 empty] | A |  |  |  |  | CostAccounting | Low/No Risk | Completed
G8-1.2 | Customer Notification | Receive customer feedback | Lessons Learned Corner | [14 empty] | A |  |  |  | A |  | R | [5 empty] | A | [6 empty] | In progress
Note on AM4: ====== ID#AAABOlc7NVM tc={8DD592E7-7EF3-4857-BD9E-0AFC858F56B2} (2021-11-15 14:23:55) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please, select one of the options: 1-Done 2-Ongoing, Low risk 3-Ongoing, Medium risk 4- Ongoing, High risk

## Action Plan
FORM-0003 Rev 6.0 |  |  | Please move actions as quickly as possible to JIRA and label properly for easy retrieval. This sheet gets stale quickly. |  |  |  | FORM-0003 Rev 5.0
| Gate Review | Action # | Action task Description | Responsible | Due Date | JIRA# | JIRA Status
| Gate 0 | A1 | Review Package Cost model due to concerns about 2nd source availability and wirebonds costs | Package Engineer | <before next ML | PROJ-091
| Gate 0 | A2
| Gate 0 | A3
| Gate 0 | A4
| Gate 0 | A5
| Gate 0 | A6
| Gate 0 | A7
| Gate 0 | A8
| Gate 0 | A9
| Gate 0 | A10
| Gate 0 | A11
| Gate 0 | A12
| Gate 0 | A13
| Gate 0 | A14
| Gate 0 | A15
| Gate 0 | A16
| Gate Review | Action # | Action task | Responsible | Due Date | Jira# | JIRA Status
| Gate 1 | A17
| Gate 1 | A18
| Gate 1 | A19
| Gate 1 | A20
| Gate 1 | A21
| Gate 1 | A22
| Gate 1 | A23
| Gate 1 | A24
| Gate 1 | A25
| Gate 1 | A26
| Gate 1 | A27
Note on G2: ====== ID#AAAAWb5Rcts Lionel (2022-03-03 03:16:48) Add JIRA ticket for actionable tasks.
Note on H19: ====== ID#AAAAQ-Fmh68 tc={4A6F4F03-D094-4419-A8D6-9E55BA3196FC} (2021-10-18 12:11:14) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Open Ongoing Done

## Definitions
A RASCI chart is a simple matrix used to assign roles and responsibilities for each task, milestone, or decision on a project. By clearly mapping out which roles are involved in each project task and at which level, you can eliminate confusion and answer the age-old project question, Who’s doing what?
R: Responsible | Owner | A role charged with leading the origination and completion of the document work product
A: Approves | Must Sign Off | A role that is identified as a mandatory approver of the work product
S: Supports |  | A role of management escalation available to facilitate activities related to the work product
C: Contributes | Knowledge & Capability to complete the task | A role that works with the responsible party to complete aspects of the work product. The person who has the ability or knowledge needed to complete the work. This person needs to be asked for feedback, and feedback needs to be taken into account.
I: Informed | Must be notified of results | A role that requires to be informed of progress on the work product
Cheklist Item Status | Provide input wrt the status of the checkpoint in the context of the gate review
Chekcklist Item Risk | Overall risk weight for this checkpoint. A high risk should lead to a fail of the gate review or a strong mitigation plan.
JIRA tasks | JIRA tasks should be recorded for actional tasks that must be taken by the organization. A JIRA should not be entered as a reminder for the program Manager. Action Plan should suffice.
Action Plan Items | When action plan item is closed,related checkpoint's risk and status column need to be re-assessed.

## Template History
FORM-0003 Rev 5.0
Author | Date | Change Description | Change Gx-y.z | JIRA | Release
Frank (added by Lionel) | 2022-03-09 | Physical Checks completed - final physical checks (technical tape-out checklist) released. Follow chip level checklist | G3-2.4 added
Lionel | 2022-03-09 | Design for Test and Design for Manufacturing - Design Analysis to extract a Target Yield based on Foundry D0, digital contents, etc... | G3-5.5 added | http://jira:8080/browse/QA-214
Lionel | 2022-03-09 | Added cost model update at each key gate review (G0, G1, G2, G3, G4, G5, G6) | G0-4.5 G1-4.6 G2-5.3 G3-9.4 (not new) G4-6.4 G5-7.5 G6-5.4
Lionel | 2022-03-09 | G1-4 items reoptimized (redundancy with other items) | G0.3.4
Lionel | 2022-06-03 | G0.3.4 added, Reviewed SOP-0007 and updated a few items in FORM0003 to match - Goal is to remove the checkpoints for SOP-0007
Lionel | 2022-06-17
lionel | 2022-07-28 | Supplier PPAP - move supplier engineering change review to G5.x from G6-3.3
Lionel | 2022-08-30 | Clean Up the Gate Review Check point - Team need to refer to SOP 0007 for the signature list. The RASCI in FORM0003 list the people that own the checkpoint. |  |  | 3.1
Lionel | 2022-08-30 | Added draft G0.8 checklist |  |  | 3.1
Lionel | 2022-09-01 | added column Category |  |  | 3.1
Lionel | 2022-09-01 | Added Package engineer in RASCI |  |  | 3.1
Lionel | 2022-09-01 | Added various template links |  |  | 3.1
Lionel | 2022-09-01 | G1-6.1 split checpoint for package engineer, foundry process reliability engineer. |  |  | 3.1
Lionel | 2022-09-01 | moved -ATE HW and SW resources required assessed/listed -Risks related to test time and coverage assessed in G1.7x |  |  | 3.1
Lionel | 2022-09-01 | reworked Rasci G2-G5 |  |  | 3.1
Lionel | 2022-09-01 | added G2 SCM generation dedicated line (was in DFT Before). |  |  | 3.1
Lionel | 2022-09-01 | swaped G3.2x and G3.3x (design first, physical checks second) |  |  | 3.1
Lionel | 2022-09-01 | rephrased G3-1.1 - align with actual practice |  |  | 3.1
Lionel | 2022-09-01 | split DVT and System tests in G3 - renamed G3.x numbers |  |  | 3.1
Lionel | 2022-09-01 | moved fmea under project management in G4 |  |  | 3.1
Lionel | 2022-09-01 | G5.4.x created for ATE test related stuffs |  |  | 3.1
Lionel | 2022-10-24 | Added Milestone Trend Analysis (MTA) sheets. This MTA sheet will need to be update at every gate review and more frequently as needed. |  |  | 3.3
Lionel | 2022-11-29 | gate review: commented the fact that list of approvers and attendees is documented in SOP-0007. |  |  | 4.1
Lionel | 2022-12-12 | G2-2.1 G2-2.5 updated to give better guidelines to team
Lionel | 2023-02-10 | Added link to smartsheet template for G1-4.6
Lionel | 2023-06-13 | updated Form following http://jira:8080/browse/ZUB-197 feedback (describe who generates project schedule in G0/G0.8/G1 | G0-1, G0.8-4.1, G1-5.2
Lionel | 2023-06-13 | change owner G1-6.4 to PE, change RASCI of G1-6.3 to PQE as list in checkpoint (PQE) | G1-6.4, G1-6.3
Lionel | 2023-06-15 | Update Lesson Learned check points ot point to new Confluence Space http://confluence.indiesemi.com:8090/x/MydNBw | G1-2.3, G3-10.6, G6-7.2
Lionel | 2023-08-31 | fix duplicate G1-6.3 and G1-6.4 | G1-6.4, G1-6.3
Lionel | 2023-08-31 | Added explicit link to confluence lesson learned space. | G1-2.3
Lionel | 2024-01-16 | refer to release | http://jira.indiesemi.com:8080/projects/QA/versions/11420
Lionel | 2024-01-23 | Adopted FORM-0038 RASCI definition.
Lionel | 7350429 | Cyber Security (CySe) added. Other changes tracked by jira FORM-0003 rev 6 release. | G0.8 to G6